## Agile Sprint Backlog
SPRINT BACKLOG - SPRINT 1
ID | USER STORIES/TASKS | STATUS | ASSIGNED TO | COMPLETED BY | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | A user can search based on code. | Not started | Neja |  | 9 | 1
2 | A user can search based on procedure. | Not started | Neja |  | 10 | 1
3 | A user can search based on condition. | Not started | Neja |  | 10 | 1
4 | A user can search based on location input | Not started | Ross |  | 9 | 4
5 | A user can order the search results based on price | Not started | Stas |  | 8 | 1
6 | A user can order the search results based on distance | Not started | Stas |  | 8 | 1
7 | A user can view the output of a search as a list. | Not started | Stephen |  | 10 | 3
8 | As a programmer, I want to find an API to support Google Maps for live location services. | Not started | Ross |  | 7 | 5
9 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user. | Not started | Kamila |  | 10 | 6
10 | A user can set a price range for their search. | Not started | Stephen |  | 2 | 2
11 | A user can set a distance range for their search. | Not started | Stas |  | 3 | 3
12 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data. | Not started | Kayla |  | 10 | 5
| TOTAL |  |  |  |  | 33 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog - Final Version
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | COMPLETED BY | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
A user can search based on code. | Neja |  | In progress | 9 | 1
Task
Task
Task
Task
A user can search based on condition. | Neja |  | In progress | 10 | 1
Task
Task
Task
Task
A user can search based on procedure | Neja |  | In progress | 10 | 1
Task
Task
Task
Task
A user can search based on location input | Ross |  | In progress | 9 | 4
Task
Task
Task
Task
A user can order the search results based on price | Stas |  | In progress | 8 | 1
Task
Task
Task
Task
A user can order the search results based on distance | Stas |  | In progress | 8 | 1
Task
Task
Task
Task
A user can view the output of a search as a list. | Stephen |  | In progress | 10 | 3
Task
Task
Task
Task
As a programmer, I want to find an API to support Google Maps for live location services. | Ross | Ross | Completed | 7 | 5
Task
Task
Task
Task
As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user. | Kamila |  | In progress | 10 | 6
Task
Task
Task
Task
A user can set a price range for their search. | Stephen |  | In progress | 2 | 2
Task
Task
Task
Task
A user can set a distance range for their search. | Stas |  | In progress | 3 | 3
Task
Task
Task
Task
As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data. | Kayla | Kayla | Completed | 10 | 5
Create basic home page
Create results page for search results
Edit CSS
Write input validation

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0