## Agile User Stories
USER STORIES
TASK ID | USER STORY | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | CONVERSATION | CONFIRMATION
1 | A user can search based on code. | 9 | 1 | 9 | - Stored as the first 3 digits of DRG Definition - Between 000 and 999 - Add user input validation on front end - Separate from Description when using Search (radio buttons) - Shows only entries with the exact number | - Test that the user input is only 3 digits - Test that the input does not include special characters - Test that the input field is not empty - Test that an incorrect input shows a message
2 | A user can search based on procedure. | 10 | 1 | 10 | - Stored as DRG Definition - Description might not be exact - not case sensitive - If no exact result based on lexical similarity - Ignore whitespace | - Test that the input field is not empty - Test finding an entry with exact wording - Test finding a close match is the entry does not match - Test that a message is generated if there are no matches
3 | A user can search based on condition. | 10 | 1 | 10 | - Stored as DRG Definition - Description might not be exact - not case sensitive - If no exact result based on lexical similarity - Ignore whitespace | - Test that the input field is not empty - Test finding an entry with exact wording - Test finding a close match is the entry does not match - Test that a message is generated if there are no matches
4 | A user can search based on live location. | 7 | 4 | 2
5 | A user can search based on location input. | 9 | 4 | 2
6 | A user can search based on a description of a condition. | 6 | 2 | 3
7 | A user can search based on a description of a procedure. | 6 | 2 | 3
8 | A user can order the search results based on price. | 8 | 1 | 8
9 | A user can order the search results based on distance. | 8 | 1 | 8
10 | A user can view the output of a search as a list. | 10 | 3 | 3
11 | A user can view the search results on a map. | 5 | 7 | 1
12 | A user can see the price information on a placeholder for each result on the map. | 4 | 6 | 1
13 | As a programmer, I want to find an API to support Google Maps for live location services. | 7 | 5 | 1
14 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user. | 10 | 6 | 2
15 | A user can set a price range for their search. | 2 | 2 | 1
16 | A user can set a distance range for their search. | 3 | 3 | 1
17 | A user can order the search results based on a ranking which is a combination of price, distance and user feedback. | 4 | 5 | 1
18 | The purchaser can delete data from the existing data set. | 1 |  | #DIV/0!
19 | The purchaser can load new data from the existing data set. | 1 |  | #DIV/0!
20 | The purchaser can update existing data. | 1 |  | #DIV/0!
21 | The purchaser can add data to the existing data set. | 1 |  | #DIV/0!
22 | A user can navigate with a keyboard. | 3 | 1 | 3
23 | A user can view the data regardless of colour blindness. | 3 | 2 | 2
24 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data. | 10 | 5 | 2
25 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | 10 | 7 | 1 | - Using MySQL database hosted on Azure - Whole project deployed to Azure with Web app - Java EE for backend, developed in EclipseEE - For development purposes hosted on Apache Tomcat servers - Integration between frontend and backend with JSP files - Frontend in HTML and CSS using a Bootstrap template | - Test that the database is available - Test that backend connects successfully to the database - Test that user input can be called in the JSP file and used in the Java file - Test the frontend works and is displayed correctly
26