## Agile Sprint Backlog
SPRINT BACKLOG - SPRINT 2
ID | TASK | STATUS | ASSIGNED TO | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | A user can search based on live location | Not started |  | 7 | 4
2 | A user can search based on a description of a condition. | Not started |  | 6 | 2
3 | A user can search based on a description of a procedure. | Not started |  | 6 | 2
4 | A user can view the search results on a map. | Not started |  | 5 | 7
5 | A user can see the price information on a placeholder for each result on the map | Not started |  | 4 | 6
6 | A user can order the search results based on the ranking which is a combination of price, distance and user feedback | Not started |  | 4 | 5
7 | A user can navigate with a keyboard | Not started |  | 3 | 1
8 | A user can view the data regardless of colour blindness | Not started |  | 3 | 2
| TOTAL |  |  |  | 29 | 0 | 0 | 0 | 0 | 0 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0