## Agile Sprint 2 Backlog
SPRINT BACKLOG - SPRINT 2
ID | TASK | STATUS | ASSIGNED TO | COMPLETED BY | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | As a user, I can search based on location input | Not started | Ross |  | 8 | 3 | 3
2 | As a user, I can search based on live location | Not started | Ross |  | 7 | 5 | 5
3 | As a user, I can search based on a description of a procedure | Not started | Neja, Kayla |  | 6 | 2 | 2
4 | As a user, I can view the search results on a map | In progress | Ross |  | 5 | 8 | 7
5 | As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches | In progress | Ross, Kamila |  | 4 | 3 | 1
6 | As a user, I can see the price information on a placeholder for each result on the map | Not started | Kayla, Kamila |  | 4 | 5 | 5
7 | As a user, I can order the search results based on the ranking which is a combination of price, distance | IN progress | Neja |  | 4 | 5 | 4
8 | As a user, I can navigate with a keyboard | Not started | Stas, Stephen |  | 3 | 1 | 1
9 | As a user, I can view the data regardless of colour blindness | Not started | Stas, Stephen |  | 3 | 2 | 2
10 | As a programmer, I would like to optimise a webpage based on user feedback | In progress | Kayla |  | 8 | 5 | 5
11 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | In progress | Neja, Kamila |  | 10 | 3 | 2
12 | As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code | Not started | Stas, Stephen |  | 10 | 5 | 4
| TOTAL |  |  |  |  | 47 | 41 | 0 | 0 | 0 | 0 | 0

## Detailed Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | COMPLETED BY | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I can search based on live location
Task
As a user, I can search based on location input
Task
Task
Task
As a user, I can search based on a description of a procedure
Task
Task
Task
Task
As a user, I can view the search results on a map
Task
Task
Task
Task
As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches
Task
Task
Task
Task
As a user, I can see the price information on a placeholder for each result on the map
Task
Task
Task
As a user, I can order the search results based on the ranking which is a combination of price, distance
As a user, I can navigate with a keyboard
As a user, I can view the data regardless of colour blindness
As a programmer, I would like to optimise a webpage based on user feedback
As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience
As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code
Task
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0