## Agile User Stories
USER STORIES
TASK ID | USER STORY | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | CONVERSATION | CONFIRMATION
1 | As a user, I can search based on code. | 9 | 1 | 9 | - Stored as the first 3 digits of DRG Definition - Between 000 and 999 - Add user input validation on front end - Separate from Description when using Search (radio buttons) - Shows only entries with the exact number | - Test that the user input is only 3 digits - Test that the input does not include special characters - Test that the input field is not empty - Test that an incorrect input shows a message
2 | As a user, I can search based on procedure. | 10 | 1 | 10 | - Stored as DRG Definition - Description might not be exact - not case sensitive - If no exact result based on lexical similarity - Ignore whitespace | - Test that the input field is not empty - Test finding an entry with exact wording - Test finding a close match is the entry does not match - Test that a message is generated if there are no matches
3 | As a user, I can search based on live location. | 7 | 5 | 1 | Ensure permission is asked. Check if the user is in the US. | Test that the map display the correct location of the device on the results page
4 | As a user, I can search based on location input. | 9 | 4 | 2 | Only allow locations in the US. | Test that the map displays the correct location on the results page.
5 | As a user, I can search based on a description of a procedure. | 6 | 2 | 3 | Use keywords within the input to compare semantic similarity | Test that keywords are displayed in results
6 | As a user, I can order the search results based on price. | 8 | 1 | 8 | Unit of measurement = USD ($) Results will be ordered by price (lowest -> highest) by default | Test that the lowest value is displayed first.
7 | As a user, I can order the search results based on distance. | 8 | 1 | 8 | Unit of measurement = kilometers (km) Always order lowest -> highest | Test that the lowest value is displayed first.
8 | As a user, I can view the output of a search as a list. | 10 | 3 | 3 | Don’t need to display all columns from the database, only relevant columns necessary. | Test that inputting a query will display the results in list format on the next page (results page)
9 | As a user, I can view the search results on a map. | 5 | 8 | 1 | Will require the implementation of a maps API | Test that the map appears on the page and is dynamic.
10 | As a user, I can see the price information on a placeholder for each result on the map. | 4 | 5 | 1 | Unit of measurement = USD ($). | Test when clicking on a marker than the placeholder shows the price information from the data set provided.
11 | As a programmer, I want to find an API to support Google Maps for live location services. | 7 | 5 | 1 | Research to be done into the different types of APIs to support maps and ensure no charges will occur from usage. | n/a
12 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user. | 10 | 6 | 2 | Using a mySQL database and hosted on MS Azure | Test a mySQL stored procedure to select all data to ensure all data was imported correctly
13 | As a user, I can set a price range for their search. | 2 | 2 | 1 | Unit of measurement = USD ($) Default values to be used if no input taken. | Test with a minimum and a maximum price value, check all results fall within the range. Test that minimum cannot be below 0. Test that maximum cannot be above $1,000,000 Test that minimum is less than maximum. Test that default values are used if only one of these values is entered by the user.
14 | As a user, I can set a distance range for their search. | 3 | 3 | 1 | Unit of measurement = kilometers (km) Default values to be used if no input taken. | Test with a minimum and a maximum distance value, check all results fall within the range. Test that minimum cannot be below 0. Test that minimum is less than maximum. Test that default values are used if only one of these values is entered by the user.
15 | As a user, I can order the search results based on a ranking which is a combination of price, distance and user feedback. | 4 | 5 | 1 | User feedback will not be included as we do not have access to any, outwith project scope. | Assigned to sprint 2, team have not yet discussed how the ranking will be calculated.
16 | As a purchaser, I can delete data from the existing data set. | 1 |  |  | Discussed and decided outwith scope of project. | n/a
17 | As a purchaser, I can load new data from the existing data set. | 1 |  |  | Discussed and decided outwith scope of project. | n/a
18 | As a purchaser, I can update existing data. | 1 |  |  | Discussed and decided outwith scope of project. | n/a
19 | As a purchaser, I can add data to the existing data set. | 1 |  |  | Discussed and decided outwith scope of project. | n/a
20 | As a user, I can navigate with a keyboard. | 3 | 1 | 3 | n/a | Test the main webpage using the keyboard as navigation, ensure every box/button can be accessed/edited
21 | As a user, I can view the data regardless of colour blindness. | 3 | 2 | 2 | n/a | Will run the system through colour blindness checkers online
22 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data. | 10 | 5 | 2 | Will need to include HTML, CSS and JavaScript files | Test that all files can access each other correctly so that formatting and any JS functions work in the main webpage
23 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | 10 | 7 | 1 | - Using MySQL database hosted on Azure - Whole project deployed to Azure with Web app - Java EE for backend, developed in EclipseEE - For development purposes hosted on Apache Tomcat servers - Integration between frontend and backend with JSP files - Frontend in HTML and CSS using a Bootstrap template | - Test that the database is available - Test that backend connects successfully to the database - Test that user input can be called in the JSP file and used in the Java file - Test the frontend works and is displayed correctly
24 | As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches | 4 | 3 | 1
25 | As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code | 10 | 5 | 2
26 | As a programmer, I would like to optimise a webpage based on user feedback | 8 | 5 | 2