## Agile Sprint 1 Backlog
SPRINT BACKLOG - SPRINT 1
ID | USER STORIES/TASKS | STATUS | ASSIGNED TO | COMPLETED BY | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | A user can search based on code | Completed | Neja | Neja | 9 | 1 | 1 | 1 | 1 | 0 | 0
2 | A user can search based on procedure/condition | Completed | Neja | Neja | 10 | 1 | 1 | 1 | 3 | 3 | 0
3 | A user can search based on location input | Not started | Ross |  | 9 | 4
4 | A user can order the search results based on price | Not started | Stas |  | 8 | 1
5 | A user can order the search results based on distance | Not started | Stas |  | 8 | 1
6 | A user can view the output of a search as a list | Not started | Stephen |  | 10 | 3
7 | As a programmer, I want to find an API to support Google Maps for live location services | Not started | Ross |  | 7 | 5
8 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user | Not started | Kamila |  | 10 | 6
9 | A user can set a price range for their search | Not started | Stephen |  | 2 | 2
10 | A user can set a distance range for their search | Not started | Stas |  | 3 | 3
11 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | Not started | Kayla |  | 10 | 5
12 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | In progress | Neja, Kamila | Neja, Kamila, Kayla | 10 | 7 | 7 | 7 | 5 | 3 | 3
| TOTAL |  |  |  |  | 39 | 9 | 9 | 9 | 6 | 3 | 0

## Detailed Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | COMPLETED BY | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
A user can search based on code | Neja | Neja | Completed | 9 | 1 | 1 | 1 | 3 | 3 | 0
Write SQL Query |  | Neja |  |  |  | 1 | 0 | 0 | 0 | 0
Parse information from the input form to JSP file |  | Neja |  |  |  | 1 | 1 | 1 | 0 | 0
Call Java functions with selected parameters and query |  | Neja |  |  |  | 1 | 1 | 3 | 3 | 0
A user can search based on condition/procedure | Neja | Neja | Completed | 10 | 1 | 1 | 1 | 1 | 3 | 0
Write SQL Query |  | Neja |  |  |  | 1 | 0 | 0 | 0 | 0
Parse information from the input form to JSP file |  | Neja |  |  |  | 1 | 1 | 1 | 0 | 0
Call Java functions with selected parameters and query |  | Neja |  |  |  | 1 | 1 | 3 | 3 | 0
A user can search based on location input | Ross |  | In progress | 9 | 4
Task
Task
Task
Task
A user can order the search results based on price | Stas |  | In progress | 8 | 1
Task
Task
Task
Task
A user can order the search results based on distance | Stas |  | In progress | 8 | 1
Task
Task
Task
Task
A user can view the output of a search as a list | Stephen |  | In progress | 10 | 3
Task
Task
Task
Search returns a formatted list of all results |  | Neja | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
As a programmer, I want to find an API to support Google Maps for live location services | Ross | Ross | Completed | 7 | 5
Task
Task
Task
Task
As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user | Kamila |  | In progress | 10 | 6
Task
Task
Task
A user can set a price range for their search | Stephen |  | In progress | 2 | 2
Task
Task
Task
Task
A user can set a distance range for their search | Stas |  | In progress | 3 | 3
Task
Task
Task
Task
As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | Kayla | Kayla | Completed | 10 | 5
Create basic home page
Create results page for search results
Edit CSS
Write input validation
As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | In progress | Neja, Kamila | Neja, Kamila, Kayla | 10 | 7 | 9 | 9 | 7 | 5 | 1
Connecting Java backend to the database (JDBC Driver) |  | Neja, Kamila | Neja, Kamila |  |  | 3 | 3 | 3 | 0 | 0
Connecting JSP to the Java backend |  | Neja, Kamila | Neja, Kamila |  |  | 2 | 2 | 2 | 2 | 0
Connecting HTML to JSP |  | Neja, Kamila, Kayla | Neja, Kamila, Kayla |  |  | 1 | 1 | 1 | 1 | 0
Adding CSS and JS to the webiste |  | Kamila, Kayla | Kamila, Kayla |  |  | 2 | 2 | 2 | 2 | 1
Connecting to the server (Apache Tomcat) |  | Neja, Kamila | Neja, Kamila |  |  | 1 | 1 | 1 | 0 | 0