## Agile Product Backlog
PRODUCT BACKLOG
ID | USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | STATUS
1 | A user can search based on code | 1 | Neja | 29th Jan | 30th Jan | 9 | 1 | 9 | Completed
2 | A user can search based on procedure/condition | 1 | Neja | 30th Jan | 30th Jan | 10 | 1 | 10 | Completed | Completed
3 | A user can search based on live location | 2 |  |  |  | 7 | 4 | 2 | Not Started | Not Started
4 | A user can search based on location input | 1 |  |  |  | 9 | 4 | 2 | Not Started | In Progress
5 | A user can search based on a description of a condition/procedure | 2 |  |  |  | 6 | 2 | 3 | Not Started
6 | A user can order the search results based on price | 1 | Stas | 26th Jan | 27th Jan | 8 | 1 | 8 | Completed
7 | A user can order the search results based on distance | 1 | Stas | 26th Jan | 27th Jan | 8 | 1 | 8 | Completed
8 | A user can view the output of a search as a list | 1 |  |  |  | 10 | 3 | 3 | Not Started
9 | A user can view the search results on a map | 2 |  |  |  | 5 | 7 | 1 | Not Started
10 | A user can see the price information on a placeholder for each result on the map | 2 |  |  |  | 4 | 6 | 1 | Not Started
11 | As a programmer, I want to find an API to support Google Maps for live location services | 1 |  |  |  | 7 | 5 | 1 | Not Started
12 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user. | 1 |  |  |  | 10 | 6 | 2 | Not Started
13 | A user can set a price range for their search | 1 |  |  |  | 2 | 2 | 1 | Not Started
14 | A user can set a distance range for their search | 1 | Stas | 27th Jan | 30th Jan | 3 | 3 | 1 | Completed
15 | A user can order the search results based on the ranking which is a combination of price, distance and user feedback. | 2 |  |  |  | 4 | 5 | 1 | Not Started
16 | The purchaser can delete data from the existing data set | n/a |  |  |  | 1 |  |  | Not Started
17 | The purchaser can load new data from the existing data set | n/a |  |  |  | 1 |  |  | Not Started
18 | The purchaser can update existing data | n/a |  |  |  | 1 |  |  | Not Started
19 | The purchaser can add data to the existing data set | n/a |  |  |  | 1 |  |  | Not Started
20 | A user can navigate with a keyboard | 2 |  |  |  | 3 | 1 | 3 | Not Started
21 | A user can view the data regardless of colour blindness | 2 |  |  |  | 3 | 2 | 2 | Not Started
22 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | 1 |  |  |  | 10 | 5 | 2 | Not Started
23 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | 1 | Kamila | 27th Jan |  | 10 | 7 | 1 | In Progress